## Sheet1
Task Name | Start Week | Target End Week | Status | Estimated Work Hours | Logged Work Hours | Notes | Total Estimated Hours | Total Complete Hours | Percent Complete
Initial Project Planning | [6 empty] | 80 | 2 | 2.5%
Task Diagram First Iteration | Week 1 | Week 1 | Complete | 1 | 1 | This should not take long but may be changed later on
GitHub repo creation | Week 1 | Week 1 | Complete | 2 | 1 | The creation included the other starting documentation needed
Primary Development
Initialization/ Map Generation Algo | Week 2 | Week 2 | Not Started
LCD Display setup and config | Week 2 | Week 2 | Not Started
Quantum Disruptor/ LED Driver Task | Week 2 | Week 2 | Not Started
Physics Engine/ Gyro sampler | Week 2 | Week 3 | Not Started
Collision Detection Task | Week 3 | Week 3 | Not Started
Game Logic Task | Week 3 | Week 3 | Not Started
Testing and Validation
LCD and UI testing | Week 2 | Week 3 | Not Started |  |  | Expected Output: LCD displays current game state and maze, UI is easily interpretable by other students.
Physics Engine Testing | Week 2 | Week 3 | Not Started |  |  | Expected Output: Ball position correclty responds to tilting of board. Other tasks can acces positional data
Quatum Disruptor Testing | Week 2 | Week 3 | Not Started |  |  | Expected Output: Button interrupt correctly triggers timer to depleted disruptor charge.
Collision Detection testing | Week 3 | Week 3 | Not Started |  |  | Expected Output: Ball correctly collides with walls and holes, unless disruptor has charge and activated
Game Logic Tetsing | Week 3 | Week 3 | Not Started |  |  | Expected Output: Waypoints correctly selected, game correctly responds to win conditions.
Project Reporting
Weekly progress report | Week 1 | Week 4 | Not Started
Final Project Report | Week 4 | Week 4 | Not Started