## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
I catch CoViD | 100 | 40 | 4000 | 2024-03-22 | Mitigated | M | learned instructor has extension possible
My gecko is not working | 1 | 1 | 1 | 2024-03-22 | N/A | O | Test it. If mine not working, contact instructor
Maze generation causes error | 40 | 40 | 1600 | 2024-03-22 | N/A | O | Test alogrithm, if having difficulties ask TA or other students for assitance
Physics Model bugs | 40 | 70 | 2800 | 2024-03-22 | N/A | O | Test alogrithm, if having difficulties ask TA or other students for assitance
LCD Display bugs | 40 | 20 | 800 | 2024-03-22 | N/A | M | Test it. If mine not working, contact instructor
Collision Task bugs | 70 | 70 | 4900 | 2024-03-22 | N/A | O | Test alogrithm, if having difficulties ask TA or other students for assitance
Game end condition bugs | 40 | 70 | 2800 | 2024-03-22 | N/A | O | May need to iteratively test and fine tune game logic parameters
Gyro sampling not fast enough | 20 | 20 | 400 | 2024-03-22 | N/A | M | May need to experimentally determine optimal clock speed
Ball status atomicity not implemented correctly | 20 | 70 | 1400 | 2024-03-22 | N/A | O | May need to rework the usage of mutexes and semaphores
Deadlock/problem with scheduling chosen | 8 | 100 | 800 | 2024-03-22 | N/A | M | Test it, if occuring reach out to TA or professor for advice
Disruptor bug | 40 | 40 | 1600 | 2024-03-22 | N/A | O | Test alogrithm, if having difficulties ask TA or other students for assitance
Task stack size not large enough | 40 | 40 | 1600 | 2024-03-22 | N/A | M | Test it, if occuring reach out to TA or professor for advice

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100